## Sheet1
Task Name | Assignee | Task Status | Expected Time | Actual Time
dio | atef | done | 16/5 | 16/5
timers | atef | done | 16/5 | 16/5
pwm | atef | done | 16/5 | 16/5
icu | atef | done | 16/5 | 16/5
Interrupt | atef | done | 15/5 | 15/5
motor | amr | done | 15/5 | 15/5
lcd | atef | done | 16/5 | 16/5
US | atef | done | 15/5 | 16/5
keypad | anas | done | 15/5 | 16/5
buttons | anas | done | 15/5 | 16/5
documintation | anas/khaled | done | 18/5 | 20/5
application | team | done | 18/5 | 19/5